LOVE YOURSELF NOW: LAUNCH PLAYBOOK

Developed by Ascend Consulting LLC – Brad Stave, MBA
October 4, 2026

Soaring Dragonfly Institute event launch for Camella McBrayer, Imeko Woods and Von-Na Chism

This playbook is built around one event: Love Yourself Now, Thursday, November 5, 6:30 to 8:30 PM, Central Co-op, 4502 N Pearl St, Tacoma. It goes with the launch package of flyers, graphics and the outreach workbook. You can start outreach Monday, October 5.

1. Start here

| Piece | Where it is | Use it for |
| --- | --- | --- |
| Redesigned flyer, front and back | 01-Flyer / SDI_Flyer_2-Page_Print.pdf | Printing at 8.5 x 11, handing out, emailing |
| Rack card, 4 x 9 | 02-Print-Leave-Behinds / SDI_Rack_Card_4x9_Front-Back.pdf | Leaving at counters and front desks |
| Bulletin board poster with tear-off tabs | 02-Print-Leave-Behinds / SDI_Bulletin_Poster_8.5x11.pdf | Cafes, studios, libraries, community boards |
| Website banner, desktop and mobile | 03-Website-Banners | Top of your homepage, pointing to registration |
| Facebook event cover, posts, stories, link image | 04-Social-Graphics | The posting calendar in section 6 |
| Outreach workbook | SDI_Outreach_Workbook.xlsx | 52 places to visit, 55 online channels, 27 listing sites, a dated checklist |

Your first three moves on Monday:

- Test your registration page end to end (see section 2, this one matters most).

- Upload the website banner above the registration form, and create the Facebook Event.

- Walk the Priority A places in the 6th Ave and Proctor clusters with rack cards and posters.

Print tip: the PDFs are letter size with no bleed, so any print shop can run them as is. For the poster, cut the tabs apart after printing.

2. Update your website registration form

Your website still shows an "Early Bird $35" line and a Register button, plus two "Custom price" fields. Every piece in this package says the event is a free launch with a suggested donation, so the site needs to be updated to match before anything goes out. Change the form to a free RSVP with an optional donation (suggested $35 early bird through Oct 29, $50 advance, $60 at the door), then run a test sign-up. Until the site matches, anyone who scans a QR code will see a different message than the flyer.

3. Who we are reaching and the message

The target is driven, high-performing adults who already invest in their own wellbeing and have not yet found a place where self-kindness is practiced, not just discussed. Three groups make up most of that audience.

| Who | What they are doing now | Where to find them | What gets them to sign up |
| --- | --- | --- | --- |
| The tired high performer: managers, founders, professionals, perfectionists | Working a lot, saying yes too often, feeling flat or on edge, taking care of everyone but themselves, too busy to hear themselves think, always tuned in to everyone else | Coworking spaces, professional and women's networking groups, small business groups on Facebook | A low-pressure, two-hour, no-commitment evening that respects their time |
| The movement and wellness regular | Takes classes, already invests in support, wants community that is not a class | Movement studios, wellness practices, meditation centers | Honest sharing in a small circle, plus gentle movement and journaling |
| The journaler and book-club reader | Reads self-growth books, drawn to The Artist's Way | Bookstores, libraries, book-club groups, creative groups | A book-club format they can join without having read anything |

The message in one line: a grown-up circle time where you practice hearing yourself first, led by Credentialed Guides with Lived Experience. Free launch. A $497 value. Suggested donation: $35 early bird through Oct 29, $50 advance, $60 at the door.

A. Hooks to rotate

- You hear everyone else. Somewhere along the way, you stopped hearing yourself.

- When did you last hear yourself think?

- You listen to everyone. Who listens to you?

- Your voice got quiet. Even inside.

- It never left. Come practice hearing it.

Proof you can state: Credentialed Guides with Lived Experience, a venue and a date. Do not claim outcomes, because one anonymous quote is not evidence and the event is a practice, not a treatment.

B. Wording rules for all marketing (from Camella)

- Avoid "therapy," "therapeutic," "treatment," "clinical," "healing" and "heal." Use "practice," "cultivate resilience" and "self-kindness."

- Call the final activity a "closing practice."

- Do not mention Medicaid or insurance billing anywhere in marketing.

- Say "participant," never "client."

- Credit Julia Cameron and italicize The Artist's Way every time it appears.

- Never promise a number of guides or a facilitator ratio. If enrollment goes above ten, an additional guide joins, but enrollment is unknown, so this stays internal.

- Put this exact notice on anything that describes the session.

Notice and Disclaimer: This group utilizes peer-led Experiential Wellness Practices for general personal growth and recovery support. It is facilitated by a Peer Support Specialist and is completely non-clinical. These exercises are not a substitute for experiential therapy, psychotherapy, or medical treatment. Participation does not establish a clinician-client relationship.

Where it appears: flyer back, rack card back, poster, and the two social posts that describe the session (details and guides). Use it in the Facebook Event description and in any listing that has room. Hook posts and stories carry a short caption and point to the website; add the notice wherever a post describes what happens in the session.

C. Value statement, for internal reference

Your "$497 value" rests on eight things: a Credentialed Guide with Lived Experience leading all two hours; the Montessori three-part lesson (explain, interact together, experience individually); morning pages from The Artist's Way by Julia Cameron plus two added practices, a To Do and To Be sort, and a release ceremony; gentle movement; a floor feeling wheel for nonverbal check-ins; take-home items (an Artist Date bag, a resource packet); grown-up circle time; and a complete experience in one evening. The marketing pieces carry only the short version. Keep the billing and credential details out of marketing.

4. Five week timeline

Early bird ends Thursday, October 29, one week before the event. The dated checklist with owners is on the Launch Calendar tab of the workbook. This is the shape of it.

| Week | Focus | Main actions | Checkpoint |
| --- | --- | --- | --- |
| 1: Oct 5 to 11 | Launch | Test registration, add website banner, create Facebook Event, Post 1, submit top listings (Eventbrite, Visit Tacoma-Pierce County, Tacoma Weekly, News Tribune, Daily Tacoma), walk 6 to 8 Priority A places, message Priority A group admins | Fri Oct 9: review sign-ups and source tags |
| 2: Oct 12 to 18 | Spread | Post 2, remaining listings, second walking cluster, post in approved groups (two per day at most), leave brochure-swap letters | Count of places that agreed to display |
| 3: Oct 19 to 25 | Deepen | Post 3 and a story, personal invites, second visits, Priority B places | Thu Oct 22: decision point against your sign-up goal |
| 4: Oct 26 to Nov 1 | Early bird push | Countdown story, "early bird ends Thursday" posts, Oct 29 last call | Sign-ups at early bird deadline |
| 5: Nov 2 to 6 | Convert and show up | Post 4, reminder message to everyone registered, day-before post, event, survey, thank-you | Attendance versus sign-ups, survey results |

5. In-person outreach playbook

Walk in, be brief, leave something useful. The Visit Plan tab lists 52 places by walking cluster and priority, with the right person to ask for. Names, hours and flyer policies could not be verified ahead of time, so expect to adjust.

A. What to bring

50 rack cards, 20 posters with tape, 10 flyers, your business cards, a pen, and brochure-swap letters (text below). Visit mid-morning or early afternoon, outside class and lunch rushes.

B. The 30-second pitch

Hi, I'm Camella with Soaring Dragonfly Institute. On Thursday, November 5 we're hosting a free evening circle in North Tacoma: a grown-up, book-club style night of journaling, gentle movement and reflection, led by Credentialed Guides with Lived Experience. It's a chance to practice hearing yourself first. Suggested donation is $35 early bird through Oct 29, $50 advance, $60 at the door. Could I leave a few cards at your counter, and would you be open to posting this on your board?

C. Adjust the ask by place type

| Place | Ask for | Lead with | Leave |
| --- | --- | --- | --- |
| Movement and pilates studios | Studio manager or owner | "Your students already care about this. It is free, and it complements your classes." | Poster, rack cards, and a request to mention it in class or in their email list |
| Wellness practices and studios | Office manager or the practitioner | "This is an experiential wellness practice for general personal growth, and the full notice is printed on every piece." | Rack cards for the waiting area; offer to swap brochures |
| Cafes, bookstores, libraries | Manager or the person who runs the community board | "It is a free community event with a book-club feel." | Poster only, unless they have a card rack |
| Networking groups and chambers | Membership or events coordinator | "A free evening for members who take care of everyone but themselves." | Flyer, and a request for a newsletter or event listing mention |
| Florists, boutiques, gift shops in Proctor and 6th Ave | Owner | "A neighborhood event two minutes away." | Poster and rack cards |

D. If they say no or "I'll have to ask"

Thank them, leave one rack card, and write the contact name in the Visit Plan tab. Do not push. A polite no is normal, and some places have strict flyer rules.

E. Resource table invitation

Print on your letterhead and leave it with a rack card.

Dear [name],

We are hosting Love Yourself Now, a free community circle on Thursday, November 5, 6:30 to 8:30 PM at Central Co-op, 4502 N Pearl St, Tacoma. We will have a small resource table at the event and would be glad to display brochures, cards or flyers from like-minded local businesses and practices. The event is a free launch. A $497 value. Suggested donation: $35 early bird through Oct 29, $50 advance, $60 at the door. Displaying materials costs nothing and gives your work exposure to an audience that cares about wellbeing. If you would like to take part, please leave a small stack with us by Wednesday, November 4, or email soaringdragonflyinstitute@gmail.com and we will arrange a pickup.

With thanks,

Camella McBrayer, Founder, Soaring Dragonfly Institute

F. After each visit

Update the Status column, write down the contact's name, and note whether to return. A thank-you message within two days to anyone who agreed to display or share works better than a second cold visit.

6. Social media and listings playbook

Reality check: your Facebook page has about 44 followers and its newest post is from January 2024. Posting on your own page will reach very few people. The growth path is other people's audiences: free event calendars, community groups, partner businesses, and personal invites. The Social Groups tab lists 55 channels, including 17 Facebook groups I confirmed exist and their member counts as of October 4. Group rules could not be read from outside, so check each group's rules before posting.

A. Rules that keep you from being removed

- Message the admin first where the workbook says so. Post once per group, never the same day in many groups.

- Join and take part a little before you promote. Post as yourself, name the Institute, and keep the language plain.

- Use a Facebook Event link instead of a long post where the group allows it, and answer comments quickly.

- Skip groups with a specific purpose that is not yours (recovery, faith, dads, neighborhood councils) unless an admin invites you.

B. Facebook Event description (paste as is)

Love Yourself Now: Acknowledging Reality with Hope

You hear everyone else. Somewhere along the way, you stopped hearing yourself. Find your voice. It never left. Come practice hearing it.

A grown-up circle time, book-club style, for honest sharing and connection. Participants write morning pages from The Artist's Way by Julia Cameron (with two added practices), find words for what they feel, and reconnect with the body through gentle movement. A refreshment break and a closing practice are included. No experience needed, and no pressure to share more than you want to.

Thursday, November 5, 6:30 to 8:30 PM. Central Co-op, 4502 N Pearl St, Tacoma, WA 98407. Free launch. A $497 value. Suggested donation: $35 early bird through Oct 29, $50 advance, $60 at the door.

Led by Credentialed Guides with Lived Experience: Von-Na Chism, Imeko Woods and Camella McBrayer.

Register: soaringdragonflyinstitute.com

Notice and Disclaimer: This group utilizes peer-led Experiential Wellness Practices for general personal growth and recovery support. It is facilitated by a Peer Support Specialist and is completely non-clinical. These exercises are not a substitute for experiential therapy, psychotherapy, or medical treatment. Participation does not establish a clinician-client relationship. The Artist's Way is a book by Julia Cameron; this event is not affiliated with the author or publisher. This event is not sponsored by Central Co-op.

C. Short listing blurb (about 45 words)

A free evening circle for journaling, reflection and gentle movement, with morning pages from The Artist's Way by Julia Cameron. Led by Credentialed Guides with Lived Experience. Thursday, Nov 5, 6:30 to 8:30 PM, Central Co-op, Tacoma. Free launch. A $497 value. Suggested donation: $35 early bird through Oct 29, $50 advance, $60 at the door. Register at soaringdragonflyinstitute.com.

D. Post calendar

Graphics are in the 04-Social-Graphics folder.

| Date | Graphic | Caption |
| --- | --- | --- |
| Mon Oct 5 | Post 1 (hook) | When did you last hear yourself think? On Nov 5 we're hosting a free evening in Tacoma to practice hearing your own voice first. Love Yourself Now, 6:30 to 8:30 PM. Details and registration: soaringdragonflyinstitute.com |
| Mon Oct 12 | Post 2 (hook) | You listen to everyone. Who listens to you? A grown-up circle time, book-club style, with journaling, gentle movement and reflection. Thursday, Nov 5, Central Co-op, Tacoma. |
| Wed Oct 14 | Post 4 (guides) | Meet your guides: Von-Na, Imeko and Camella, Credentialed Guides with Lived Experience. "Come as you are. We saved you a seat." Nov 5, Tacoma. |
| Mon Oct 19 | Post 3 (details) | Here is what the evening looks like: journaling, gentle movement, an exercise from The Artist's Way by Julia Cameron, and a break with refreshments. Free launch. A $497 value. Suggested donation: $35 early bird through Oct 29, $50 advance, $60 at the door. |
| Mon Oct 26 | Story 2 | Early bird ends Thursday. Suggested donation is $35 through Oct 29, then $50 advance and $60 at the door. |
| Thu Oct 29 | Story 2 | Last day of the early bird suggested donation. Join us Nov 5. |
| Mon Nov 2 | Story 1 | Thursday, 6:30 PM. Central Co-op, 4502 N Pearl St, Tacoma. Free launch. A $497 value. Suggested donation: $35 early bird through Oct 29, $50 advance, $60 at the door. |
| Wed Nov 4 | Facebook Event post | Tomorrow night. We saved you a seat. |
| Fri Nov 6 | Photo from the event (with permission) | Thank you to everyone who came. Next session announcement coming soon. |

E. Message to a group admin

Hi [name], I'm Camella McBrayer with Soaring Dragonfly Institute in Tacoma. We are hosting a free community wellness circle on Thursday, Nov 5 at Central Co-op, 4502 N Pearl St, and I would love to share it with your members if your group allows event posts. Here is the Facebook Event link: [link]. If you would rather I did not post, no problem at all. Free launch. A $497 value. Suggested donation: $35 early bird through Oct 29, $50 advance, $60 at the door. Thank you for running this community.

F. Nextdoor post

One per neighborhood, from a Business Page where possible.

Neighbors, we're hosting a free evening circle on Thursday, Nov 5, 6:30 to 8:30 PM at 4502 N Pearl St: journaling, gentle movement and reflection, led by Credentialed Guides with Lived Experience. Free launch. A $497 value. Suggested donation: $35 early bird through Oct 29, $50 advance, $60 at the door. Details: soaringdragonflyinstitute.com

G. Personal invite (text or email to your own contacts)

I'm hosting a free evening on Nov 5 in Tacoma, a grown-up circle with journaling, gentle movement and reflection. No experience needed. Would you come, or know someone who should? Details here: soaringdragonflyinstitute.com. If you can forward it to two people, that helps more than anything.

7. Measuring results

Set a sign-up goal today. The consultation hoped for 10 attendees. Free events lose a share of sign-ups on the night, so a working assumption is to collect roughly twice your attendance target (about 20 sign-ups for 10 people). That ratio is a rule of thumb, not a measured figure for your audience, so adjust it after this first event.

Know which channel worked. Each QR code in the print pieces carries a source tag (flyer, rack card, poster, web). Add one question to your registration form: "How did you hear about this?" Then record the answer in a simple tally.

Decision point, Thursday October 22: if sign-ups are well under half of goal, spend the final two weeks on personal invites and partner newsletters instead of more cold walk-ins. Personal asks tend to carry more weight than a poster on a wall.

Reduce no-shows: email or text everyone registered on Monday Nov 2 and Wednesday Nov 4 with the time, address, parking and what to bring.

Short feedback survey (hand out at the end, five questions):

- How did you hear about tonight? (flyer, friend, Facebook, a business, other)

- What was most valuable about the evening?

- What would you change?

- Would you come to another session? (yes, maybe, no)

- May we quote your comments anonymously? (yes, no)

Question 5 gives you real, permitted testimonials for the next event.

8. Risks, claims and compliance

This is not legal advice. It is a checklist to review before printing.

| Risk | What to do |
| --- | --- |
| "Free" versus a form that charges | Update the website registration form to a free RSVP with an optional donation before anything goes out. See section 2. |
| Wording and the notice | Follow the wording rules in section 3 and keep the exact notice on anything that describes the session, including the website event page and registration page. |
| Billing and credentials | Your credential and billing details, and any mention of Medicaid or insurance, stay out of all marketing. |
| Testimonials | Use only quotes from people who agreed, and prefer the survey question 5 route for future quotes. |
| Book and author | The Artist's Way and Julia Cameron are named only as the source of one exercise. The cover appears small on the front flyer. The back of the flyer now states that the event is not affiliated with the author or publisher. Drop the cover if anyone objects. |
| Venue | The flyer says the event is not sponsored by Central Co-op. Keep it on every piece. Ask the venue about posting and capacity. |
| Photos | Get permission before posting photos of attendees on November 5. |
| Trademark | The wordmark carries the TM symbol as on your logo. Your website shows a registered mark in one place and TM in another, so pick one and use it consistently. |
| Group rules | Posting against a group's rules can get you removed. Read rules and message admins first. |

9. Website, Facebook page and design notes

The live site and the Facebook page were reviewed. These are the issues that cost you sign-ups, in order of impact, with fixes that stay inside your brand.

- Registration sits below the fold. The top of the page offers "Schedule a Conversation" and a menu, and the event is nowhere in view. Put the new banner at the very top with a button that scrolls to the form.

- The page does not mention the event. No date, place or time appears in the first screen. The banner fixes this.

- Low-contrast navigation. The white menu text on the periwinkle background measures roughly 2.8 to 1, below the 4.5 to 1 accessibility standard. Use the deeper blue (#2C5B8A) or dark text for menu items.

- The logo is a boxed JPG. It sits as a white rectangle on a blue page. A transparent version would look cleaner. The new pieces use the wordmark rebuilt as live text beside your dragonfly. If you can find the original design file, swap it in for a cleaner result.

- Update the price on the form. It shows an Early Bird $35 line and custom price fields, which conflicts with the free launch message everywhere else. See section 2.

- Facebook page. The newest post is January 2024 ("New Year Special, $95"), and the page has about 44 followers. Replace the pinned post with the event, and use the event cover from the package as the page cover.

A. Design system used, so future pieces match

| Element | Value |
| --- | --- |
| Headline font | Cormorant Garamond, semibold and italic |
| Body and logo font | Lato (the wordmark matches your logo's Lato Light) |
| Primary blue | #4F80B2 (your logo), deeper #2C5B8A for text and buttons |
| Accent colors | Plum #7B5C8A, dotted lavender spiral #B896C2, green #2E7D55, aqua gradient to #DCF4F8 |
| Motifs | Your dragonfly (blue and green version), the dotted spiral, generous white space |

The old flyer used three typefaces, a heavy royal-blue block and a dense table on the back. The new one uses one serif, one sans, one accent color per page and a single call to action. The words are yours. The hierarchy is new.

Changing the date, price or venue later: update every piece together (flyer, rack card, poster, banners, social images and the website) so nothing goes out with mixed information. The editable source files are in 06-Source-Files.